## Slide 1
INTERNAL REVIEW
Weekly Product
Review
Sprint 7-8 Progress | Payment Optimization | User Center Redesign
March 31, 2026
Product Team
CONFIDENTIAL

## Slide 2
MEETING AGENDA
Today's Discussion
01
Weekly Goals Overview
Objectives & completion status
02
Core Business Metrics
KPIs & performance trends
03
User Behavior & Conversion
Funnel analysis & insights
04
Sprint 7-8 Progress
Velocity, deliverables & planning
05
Payment Optimization
Problem, solutions & timeline
06
Bug & Risk Summary
Critical issues & mitigation
07
User Center Redesign
Objectives & design comparison
08
Timeline & Dependencies
Development schedule & cross-team needs
09
Open Questions
Decisions needed & next steps
10
Summary & Action Items
Key takeaways & priorities

## Slide 3
WEEK OF MAR 24-28, 2026
Weekly Goals Overview
Payment Optimization
ON TRACK
Finalize checkout flow wireframes
Complete payment method integration spec
Stakeholder review (pending)
Progress
85%
User Center Redesign
ON TRACK
Complete 3 design concepts
User testing with 12 participants
Design decision meeting (Thu)
Progress
90%
Sprint 7 Deliverables
AT RISK
API performance improvements
Dashboard analytics module (delayed)
QA testing in progress
Progress
70%
Key Blockers
1
Analytics Module Delay
Dependency on data team schema changes - ETA Friday
2
Design Review Pending
Awaiting VP Product approval on user center direction
Success Metrics
Goals Completed
5/6
On Track
83%
Blockers
2

## Slide 4
PERFORMANCE DASHBOARD
Core Business Metrics
Week-over-week performance tracking
+12.5%
Weekly Active Users
48.2K
vs 42.8K last week
+8.3%
Conversion Rate
4.2%
vs 3.9% last week
+15.2%
Weekly Revenue
$284K
vs $246K last week
-2.1%
Avg Session Duration
8.4m
vs 8.6m last week
Weekly Trend Analysis
WAU
Revenue
Conversion

## Slide 5
CONVERSION ANALYTICS
User Behavior & Conversion Funnel
Conversion Funnel Analysis
Key Drop-off Points
Checkout Page
-28%
Users abandon at payment step
Onboarding Step 3
-18%
Profile setup complexity
Feature Discovery
-12%
Users don't explore advanced features
Optimization Opportunities
Simplify checkout
Reduce form fields, add guest checkout
Progressive onboarding
Break into smaller, manageable steps

## Slide 6
SPRINT 7 REVIEW
Sprint 7 Progress Summary
March 10-21, 2026 | 2-week sprint cycle
Committed
34
story points
Completed
28
story points
Completion
82%
sprint goal
Sprint Burndown Chart
Completed Stories
API Performance
8 pts • 40% faster
Auth Security
5 pts • 2FA added
Email Templates
3 pts • 6 templates
Analytics Module
8 pts • In progress
Velocity Trend
S4
S5
S6
S7
Avg: 27 pts/sprint

## Slide 7
SPRINT 8 PLANNING
Sprint 8 Planning & Commitments
March 24 - April 4, 2026
Sprint 8 Scope
Planned Story Points
32
Team Capacity
85%
Sprint Duration
10 days
Sprint Goal
Analytics + Payment
Team Allocation
Frontend Engineers
3 devs
Backend Engineers
2 devs
QA Engineers
1 dev
Product Designer
0.5 dev
Key Deliverables
1
Analytics Dashboard MVP
Complete dashboard module with 5 key metrics • 13 pts
2
Payment Flow Optimization
Checkout improvements & Apple Pay integration • 10 pts
3
User Center Design Finalization
High-fidelity mockups & design system updates • 5 pts
4
Bug Fixes & Tech Debt
Address 4 P2 bugs and refactoring • 4 pts
Sprint Risks
Data Schema Dependency
Data team delivery by Mar 28
Payment Provider API
Awaiting sandbox credentials

## Slide 8
INITIATIVE OVERVIEW
Payment Optimization: Problem Statement
Current Pain Points
Checkout Abandonment
28%
Users drop off at payment step, losing ~$45K/week
Limited Payment Options
3 methods
Missing Apple Pay, Google Pay, BNPL options
Form Complexity
12 fields
Average 4.2 min to complete checkout
User Feedback Highlights
"Too many form fields, feels like forever to checkout"
"Why no Apple Pay? I use it everywhere else"
"Not sure if payment went through, no confirmation"
Business Impact Analysis
Weekly Revenue Loss
$45K
Due to checkout abandonment
Annual Impact
$2.3M
Projected lost revenue
Customer Satisfaction
3.2/5
Checkout experience rating
Competitive Benchmark
Industry Avg Abandonment
18%
Top Performers
12%
Our Current Rate
28%
Opportunity: Reducing abandonment to 18% could recover $1.2M annually

## Slide 9
OPTIMIZATION STRATEGY
Payment Optimization: Proposed Solutions
Streamlined Flow
Reduce form fields from 12 to 6
Auto-fill saved payment info
One-click checkout for returning users
Progress indicator (3 steps)
Expected Impact
-8% abandon
Payment Methods
Apple Pay integration
Google Pay support
PayPal Express Checkout
Buy Now Pay Later (Klarna)
Expected Impact
+12% conversion
Trust & Clarity
Security badges & SSL indicators
Clear pricing breakdown
Real-time payment confirmation
Guest checkout option
Expected Impact
-5% abandon
Combined Expected Impact
Projected improvement from all optimizations
Abandonment Rate
28% → 15%
Revenue Recovery: +$1.2M/year

## Slide 10
IMPLEMENTATION PLAN
Payment Optimization: Timeline
Phase 1: Design & Planning
Week 1-2
Deliverables
Wireframes, user flows, tech spec
Owner
Product + Design
Status
In Progress
Phase 2: Development
Week 3-5
Deliverables
Frontend, backend, integrations
Owner
Engineering Team
Status
Pending
Phase 3: Testing & QA
Week 6
Deliverables
Unit tests, integration tests, UAT
Owner
QA Team
Status
Pending
Phase 4: A/B Testing
Week 7-8
Deliverables
50/50 split, 2-week test period
Owner
Product + Data
Status
Pending
Phase 5: Full Rollout
Week 9
Deliverables
100% traffic, monitoring setup
Owner
Engineering + Ops
Status
Pending
Success Metrics
Abandonment Rate
< 18%
Conversion Rate
> 5.5%
Checkout Time
< 2.5 min
A/B Test Plan
Control Group
Current checkout flow (50%)
Test Group
Optimized flow (50%)
Duration: 2 weeks
Sample: 10K users/group
Key Dependencies
Payment Provider
Apple Pay sandbox access by Mar 28
Security Review
Compliance sign-off required
1
2
3
4
5

## Slide 11
QUALITY ASSURANCE
Bug & Risk Summary
P0
1
Critical
P1
4
High
P2
12
Medium
P3
23
Low
Bug Trend (Last 4 Weeks)
P0 Critical Issue
PAY-284: Payment Gateway Timeout
Users unable to complete payments during peak hours (6-9 PM)
AFFECTING REVENUE
Reported: Mar 29
Action: Engineering team investigating, ETA fix: Apr 1
Top P1 Issues
USR-156: Profile Image Upload Fails
Affects 15% of users • Assigned: Sarah
DASH-89: Analytics Export Timeout
Large dataset issue • Assigned: Mike
NOT-42: Email Notifications Delayed
2-hour delay • Assigned: Lisa
Bugs Resolved This Week
18 issues closed
18

## Slide 12
RISK MANAGEMENT
Critical Risks & Mitigation Plans
R1
Payment Gateway Instability
HIGH
Impact: Revenue loss, customer complaints
Likelihood: Medium (ongoing issue)
Mitigation:
• Implement fallback payment provider
• Add retry logic with exponential backoff
• Real-time monitoring alerts
Owner: Engineering
Due: Apr 2
R2
Data Schema Delays
MEDIUM
Impact: Analytics module delayed
Likelihood: High (dependency)
Mitigation:
• Daily sync with data team
• Parallel development with mock data
• Scope reduction option identified
Owner: Product
Due: Mar 28
R3
Third-Party API Changes
MEDIUM
Impact: Payment integration breakage
Likelihood: Low-Medium
Mitigation:
• API version locking
• Automated integration tests
• Provider change management alerts
Owner: Engineering
Ongoing
R4
User Center Design Approval
LOW
Impact: Development start delayed
Likelihood: Low
Mitigation:
• Early stakeholder involvement
• Multiple design options presented
• User testing data to support decision
Owner: Design Lead
Due: Apr 3
Risk Escalation Triggers
P0 bug unresolved > 4 hours → Escalate to CTO
Sprint goal at risk > 50% → VP Product notification
Dependency delay > 3 days → Cross-team sync

## Slide 13
REDESIGN INITIATIVE
User Center Redesign: Objectives
Project Goals
Improved Information Architecture
Simplify navigation, reduce cognitive load, logical grouping of features
Enhanced Usability
Reduce task completion time by 40%, improve discoverability
Better Personalization
Contextual content, customizable dashboard, smart recommendations
Increased Engagement
Target 25% increase in feature adoption, 30% more return visits
User Research Insights
Current Satisfaction
3.4/5
Task Completion Rate
62%
Avg Time on Task
4.8 min
Key Pain Points from Users
"Can't find settings easily, buried in menus"
"Dashboard is cluttered with irrelevant info"
"Takes too many clicks to complete tasks"
"Mobile experience is frustrating"
Target Launch Date
May 15, 2026

## Slide 14
DESIGN EVALUATION
User Center Redesign: Design Comparison
Option A: Modern Minimal
CLEAN
Usability Score
4.2
Visual Appeal
4.8
Implementation
Medium
Pros:
• Clean, modern aesthetic
• High user preference (42%)
• Strong brand alignment
Cons:
• Higher dev effort
• Requires new components
Option B: Data-Dense
FUNCTIONAL
Usability Score
4.6
Visual Appeal
3.4
Implementation
Low
Pros:
• Information-rich layout
• Power user preference (35%)
• Faster implementation
Cons:
• Can overwhelm new users
• Lower visual appeal
Option C: Balanced
RECOMMENDED
Usability Score
4.7
Visual Appeal
4.5
Implementation
Medium
Pros:
• Best overall usability
• Highest user preference (52%)
• Balanced functionality
Cons:
• Moderate dev effort
• Requires careful testing
User Testing Results (n=12)
Option A Preference
42%
Option B Preference
35%
Option C Preference
52%
Recommendation
Proceed with Option C: Balanced
Best combination of usability, visual appeal, and user preference. Aligns with our goal to improve task completion while maintaining modern aesthetic.

## Slide 15
DESIGN DECISION
User Center Redesign: Recommended Approach
Selected: Option C - Balanced
Design Rationale
Combines clean visual design with functional information density. Prioritizes user task completion while maintaining modern aesthetic that aligns with brand guidelines.
Key Design Principles
• Progressive disclosure of advanced features
• Contextual actions based on user behavior
• Customizable dashboard widgets
• Consistent navigation patterns
Key Screen Mockups
Dashboard Overview
Personalized widgets, quick actions, activity feed
Settings & Profile
Tabbed navigation, grouped preferences, clear CTAs
Feature Discovery
Guided onboarding, tooltips, feature highlights
Stakeholder Feedback Summary
VP Product
"Aligns well with our user-centric goals. Clean but functional."
Engineering Lead
"Feasible within timeline. Reuses existing components where possible."
Design Team
"Strong visual hierarchy, good balance of whitespace."
Expected Outcomes
Task Completion Time
-40%
User Satisfaction
3.4 → 4.5
Feature Adoption
+25%
Return Visits
+30%
Design Approval Meeting
Apr 3, 2:00 PM

## Slide 16
PROJECT PLANNING
Development Timeline & Resource Allocation
Project Roadmap
Design
Mar 24-Apr 4
In Progress
Development
Apr 7-May 2
Pending
QA Testing
May 5-9
Pending
UAT
May 12-13
Pending
Launch
May 15
Pending
Monitor
May 16-30
Pending
Team Allocation
Frontend Engineers
2 FTE
Sarah, Mike (full-time)
Backend Engineers
1.5 FTE
Alex (full), Jordan (50%)
QA Engineers
1 FTE
Lisa (full-time from May)
Product Designer
0.75 FTE
Emma (75% allocation)
Key Milestones
Design Finalization
Apr 4 • High-fidelity mockups complete
Dev Sprint 1 Complete
Apr 18 • Core features implemented
Dev Sprint 2 Complete
May 2 • All features ready for QA
Production Launch
May 15 • 100% rollout

## Slide 17
DEPENDENCY MANAGEMENT
Cross-Team Dependencies
Dependency Matrix
Data Team
AT RISK
Analytics schema changes for dashboard module
Due: Mar 28
Owner: Data Eng
Security Team
ON TRACK
Payment flow security review and compliance sign-off
Due: Apr 4
Owner: Security
Design System
ON TRACK
New component library updates for user center
Due: Apr 2
Owner: Design Ops
Payment Provider
PENDING
Apple Pay sandbox credentials and API documentation
Due: Mar 28
Owner: Partnerships
Dependency Status Overview
2
On Track
1
At Risk
Risk Alert: Data team dependency may delay analytics module by 3-5 days if not resolved by Mar 28.
Mitigation: Parallel development with mock data; scope reduction option identified.
Communication Plan
Daily Standups
9:00 AM • Dependency blockers discussed
Weekly Sync
Tues 2:00 PM • Cross-team alignment
Slack Channel
#product-dependencies • Real-time updates
Next Dependency Review
Apr 1, 10:00 AM

## Slide 18
DECISION TRACKING
Open Questions & Decisions Needed
Pending Decisions
Q1
Analytics Module Scope
Given data schema delays, should we reduce initial scope to 3 core metrics vs 5?
DECISION NEEDED
Due: Apr 1
Recommendation: Reduce to 3 metrics to maintain timeline
Q2
Payment Provider Priority
Which payment method to prioritize if we can only launch with one: Apple Pay or Google Pay?
AWAITING INPUT
Due: Mar 31
Data: 58% iOS users vs 42% Android in our user base
Q3
User Center Launch Strategy
Should we do gradual rollout (10% → 50% → 100%) or full launch on May 15?
AWAITING INPUT
Due: Apr 3
Recommendation: Gradual rollout for risk mitigation
Resource Allocation Questions
Q4: Additional QA Resources
Current QA capacity may be insufficient for parallel testing of payment + user center features.
Request: 0.5 FTE contractor for 4 weeks
Q5: Design Support Extension
Emma's allocation drops to 50% in May. Need full-time support through launch?
Request: Extend to 100% through May 15
Timeline Adjustments
Payment Optimization
On Track
Analytics Module
At Risk (-3 days)
User Center Redesign
On Track
Decisions Needed By
Apr 3

## Slide 19
ACTION PLANNING
Next Week Priorities
April 1-4, 2026
Payment Optimization
Finalize checkout wireframes
Owner: Emma • Due: Apr 2
Technical spec review
Owner: Engineering • Due: Apr 3
Apple Pay sandbox setup
Owner: Partnerships • Due: Apr 4
User Center
Design approval meeting
Owner: Product • Due: Apr 3
High-fidelity mockups
Owner: Emma • Due: Apr 4
Analytics
Data schema decision
Owner: Product • Due: Apr 1
Dashboard component dev
Owner: Sarah • Due: Apr 4
Critical Bugs
PAY-284: Gateway timeout
Owner: Engineering • Due: Apr 1
USR-156: Profile upload
Owner: Sarah • Due: Apr 3
Key Meetings
Sprint Planning
Apr 1
10:00 AM • Define Sprint 8 scope
Design Review
Apr 3
2:00 PM • User center approval
Dependency Sync
Apr 2
10:00 AM • Data team alignment
Success Metrics
Goals to Complete
8
Critical Decisions
3
P0 Bugs to Fix
1
Focus Theme
Design Finalization

## Slide 20
SPRINT EXECUTION
Sprint 8 Action Items
March 24 - April 4, 2026
Development Tasks
Analytics Dashboard Components
13 pts
Build reusable chart components, data visualization library integration
Sarah
Due: Apr 4
Payment Flow Optimization
10 pts
Streamline checkout, reduce form fields, implement progress indicator
Mike
Due: Apr 4
User Center Design System
5 pts
Update component library, create new UI patterns
Emma
Due: Apr 2
QA & Testing
Payment Flow Testing
In Progress
Regression testing, cross-browser validation
Analytics Integration Tests
Pending
API contract testing, mock data validation
Bug Fixes
PAY-284: Gateway Timeout
P0
Implement retry logic, fallback provider
Alex
Due: Apr 1
USR-156: Profile Upload
P1
Fix image processing, add validation
Sarah
Due: Apr 3
DASH-89: Export Timeout
P1
Optimize query performance, add pagination
Jordan
Due: Apr 4
Acceptance Criteria
All stories pass QA testing
Code review approved by 2 engineers
Documentation updated
No P0/P1 bugs in production
Sprint Goal
32 pts delivered

## Slide 21
MEETING SUMMARY
Key Takeaways
Wins This Week
Revenue Growth
15.2% increase week-over-week, $284K achieved
User Growth
12.5% increase in WAU, 48.2K active users
Design Progress
User center testing complete, 52% prefer Option C
Critical Items
P0 Bug Resolution
Payment gateway timeout - fix by Apr 1
Data Dependency
Schema decision needed by Apr 1 to maintain timeline
Analytics Module
At risk of 3-day delay - scope reduction option
Decisions Made
User Center Design
Proceed with Option C (Balanced) based on user testing results
Payment Optimization
Approved for development, target launch May 15
Sprint 8 Scope
32 story points committed, pending analytics scope decision
Next Week Focus
Payment wireframes
Due Apr 2
Design approval
Due Apr 3
Analytics scope decision
Due Apr 1
Next Review
Apr 7, 2026

## Slide 22
Thank You
Questions & Discussion
Next Review
April 7, 2026
Meeting Time
10:00 AM PST
Location
Zoom / Conf Room B
All action items tracked in Jira