## Requirement Changes
Change ID | Content | Source | Date | Priority | Status
CR-012 | Add installment payment entry to payment page | Client | 3/10 | P1 | In Design
CR-013 | Add filtering to product list | Internal | 3/12 | P2 | Pending Schedule