## Slide 1
AxiomShift
B2B AI SaaS Platform
Q1 2026
CONFIDENTIAL
FINANCIAL & OPERATIONS REVIEW
Q1 Financial
Review
Pre-Audit Revenue Recognition & Cost Control Analysis
Presented by
Corporate Finance Team
March 2026
Pre-Audit Version

## Slide 2
EXECUTIVE OVERVIEW
Q1 Executive Summary
Operating Cash Flow
Positive for 2 Consecutive Quarters
Operating cash flow has achieved sustained positivity for two consecutive quarters, demonstrating improved operational efficiency and disciplined working capital management. This milestone reflects successful cost optimization initiatives and enhanced revenue quality.
R&D Cost Amortization
Within Series C Expectations
R&D cost amortization remains well within Series C funding expectations, indicating disciplined investment management and efficient resource allocation. Capital deployment aligns with strategic product roadmap milestones.
Key Performance Indicators
Cash Flow Status
POSITIVE
Consecutive positive quarters: 2
R&D Investment
ON TRACK
Variance from plan: -3.2%
Operational Efficiency
IMPROVING
QoQ improvement: +8.5%

## Slide 3
PRE-AUDIT FINANCIAL DATA
Q1 Recognized Revenue
⚠️ CRITICAL SLIDE
Total Q1 Recognized Revenue
350
M
RMB
Pre-Audit Basis
CoreRAG Subscriptions
210 n M RMB
60%
AxiomBI Deployment Services
100 M RMB
29%
Hardware & Maintenance
25 M RMB
7%
Revenue Breakdown by Segment
Note: Pre-audit figures subject to adjustment during Big Four audit process
Last Updated: March 22, 2026

## Slide 4
COST ANALYSIS
COGS & Gross Margin
Gross Margin
72%
Stabilized performance
Cloud Computing
Over Budget
+8.3% vs. plan
API Token Costs
Over Budget
+12.1% vs. plan
COGS Breakdown: Budget vs. Actual
Cost Driver Analysis
Cloud and API cost overruns driven by increased customer demand and infrastructure scaling for enterprise deployments.
Margin Stability
Despite cost pressures, gross margin stabilized at 72%, demonstrating strong pricing power and unit economics.

## Slide 5
OPERATING EXPENSES
OpEx Execution
OpEx Trend Analysis
S&M
+34.2%
Global expansion
R&D
+12.8%
Planned growth
G&A
+1.2%
Flat control
Sales & Marketing Spike
S&M expenses increased significantly due to aggressive global expansion initiatives across APAC and EMEA markets. Key investments include new regional offices, localized marketing campaigns, and enterprise sales team expansion.
G&A Remains Flat
General & Administrative expenses remain flat , indicating strong operational efficiency in back-office functions. Cost discipline maintained through process automation and shared service optimization.
Q1 OpEx Breakdown
Sales & Marketing
42%
R&D
35%
G&A
23%

## Slide 6
LIQUIDITY MANAGEMENT
Cash Runway & Burn Rate
Current Cash Runway
24
months
At current burn rate
✓ Financial Stability Maintained
Monthly Burn Rate
28.5M RMB
-12.3% vs. Q4 2025
Cash Position Trajectory
Burn Rate Optimization Initiatives
Software License Reduction
Consolidated 15 third-party tools
Vendor Consolidation
Renegotiated 8 major contracts
Cash Reserves
684M
RMB
Monthly Revenue
117M
RMB
Net Burn
-8.5M
RMB/month
Runway Target
18+
months

## Slide 7
WORKING CAPITAL
Receivables & Collection Cycle
Days Sales Outstanding
65
days
↑ 12 days vs. Q4
Total AR Balance
245
M RMB
+18% vs. Q4
DSO Target
55
days
Gap: +10 days
AR Aging Analysis
DSO Increase Drivers
DSO increased to 65 days, up from historical averages of 53 days, primarily due to enterprise customer compliance delays and extended procurement cycles for large deployments.
Collection Efficiency Metrics
Current Collections
78%
1-30 Days Past Due
15%
31-60 Days Past Due
5%
60+ Days Past Due
2%

## Slide 8
RESOURCE PLANNING
Q2 Budget Allocation
Strategic Priority
Strict Headcount Control
Q2 budget allocation prioritizes strict headcount control outside of R&D and core Sales functions to preserve cash while supporting strategic growth initiatives.
Hiring freeze: G&A, Operations, Support
Controlled growth: R&D (+8 heads)
Strategic expansion: Sales (+12 heads)
Total Q2 Budget
185M
RMB
Headcount Change
+20
Net new hires
Q2 Budget Allocation by Department
Department-Level Budget Summary
R&D
68M
37%
Sales & Marketing
75M
41%
G&A
28M
15%
Operations
14M
7%
Budget Freeze Exception: Emergency hires require CFO approval
Effective: April 1, 2026

## Slide 9
REGULATORY COMPLIANCE
Audit & Compliance Update
Big Four Audit
Currently Underway
AxiomShift has engaged a leading global accounting firm to conduct a comprehensive financial audit. The audit process is progressing according to schedule with full cooperation from all departments.
Audit Start
March 1, 2026
Expected Completion
May 15, 2026
Audit Timeline & Milestones
Planning & Scoping
Mar 1-15, 2026 ✓ Complete
Fieldwork & Testing
Mar 16 - Apr 30, 2026 ✓ In Progress
Review & Adjustments
May 1-10, 2026 ⏳ Pending
Final Report Issuance
May 15, 2026 ⏳ Scheduled
Expected Adjustments
SaaS Deferred Revenue Recognition
Minor adjustments expected on SaaS deferred revenue recognition practices to ensure full compliance with ASC 606 standards. This may impact timing of revenue recognition but not total contract value.
Revenue recognition timing adjustments
Contract modification assessments
Performance obligation evaluations
Key Audit Focus Areas
Revenue Recognition
Expense Classification
Internal Controls
Contract Reviews
Compliance Status: No material weaknesses identified to date
This presentation contains internal business information and preliminary financial figures for board discussion only. Please do not distribute externally.

## Slide 10
STRATEGIC FOCUS
Financial Priorities for Q2
PRIORITY 01
Accelerate Cash Collection
Accelerate cash collection from APAC deployments to improve working capital and reduce DSO. Focus on enterprise accounts with extended payment terms.
Target: Reduce DSO to 55 days
From current 65 days
Implement early payment incentives
2% discount for 15-day payment
Dedicated collections team for APAC
Local language support
Expected Impact
+45M RMB cash inflow
Timeline
Q2 2026
PRIORITY 02
Optimize Cloud Infrastructure ROI
Optimize cloud infrastructure ROI through rightsizing, reserved instance purchasing, and workload optimization to reduce COGS and improve gross margin.
Reserved Instance commitment
1-year RI for baseline workloads
Auto-scaling optimization
Dynamic resource allocation
Multi-cloud cost comparison
Evaluate alternative providers
Expected Savings
-15% cloud costs
Target Margin
75%
Q2 Success Metrics: DSO < 55 days | Gross Margin > 74% | Cash flow positive
Next Review: June 30, 2026