## Slide 1
Internal Document
Q1 2026
AxiomShift Q1
People Operations Review
Organization, Talent, and Workforce Planning Update
Presented by: HR Team
Departmental Submission Draft | For CFO Review & Consolidation
Confidential — Internal Use Only

## Slide 2
HR Executive Summary
Q1 2026 People Operations Overview
Organizational Stability
Q1 demonstrated stable organizational structure with 45 total employees across all functions. Leadership team remains intact with no executive departures. Reporting lines have been clarified following the Product-Engineering alignment initiative completed in January.
Departmental headcount distribution remains aligned with FY26 budget targets. Engineering (40%), Sales (27%), and Product (16%) continue as the three largest functional areas.
Hiring Progress
Q1 hiring plan was 72% achieved with 8 of 11 planned hires completed. Engineering filled 4 roles (Senior Backend, ML Engineer, DevOps, Frontend). Product added 1 PM. Sales closed 2 AE positions. HR/Recruiting hired 1 Talent Partner.
Three roles remain open: Principal Engineer, Enterprise AE, and Customer Success Manager. Average time-to-fill was 42 days, within target range.
Talent Planning
Q1 performance review cycle completed with 92% participation. Calibration sessions identified 8 high-potential employees for accelerated development tracks. Succession planning framework initiated for 3 critical leadership roles.
Skills gap analysis completed across Engineering and Product teams. Identified need for additional ML/AI expertise and senior product strategy capabilities.
Key Watch Items
Attrition rate of 6.7% (3 voluntary departures) is within industry benchmarks but requires monitoring. Two departures were in Engineering, prompting review of technical career pathways.
Manager-to-IC ratio in Engineering (1:9) approaching upper threshold. Recommend adding Engineering Manager in Q2 to maintain team effectiveness and development quality.
Document Status: Departmental Draft | Pending CFO Review

## Slide 3
Key Workforce Highlights
Headline Metrics and Strategic Indicators
45
Total Headcount
+8 net new in Q1
End of Q1: March 31, 2026
72%
Hiring Plan Achieved
8 of 11 roles filled
3 roles still open
6.7%
Voluntary Attrition
3 departures in Q1
Within industry benchmark
92%
Performance Review
Participation rate
Calibration completed
Role Prioritization Decisions
▸
Engineering: Prioritized backend and ML roles over additional frontend capacity
▸
Sales: Shifted focus to Enterprise AE from mid-market to align with ARR targets
▸
Product: Delayed second PM hire to Q2 pending roadmap clarification
▸
Customer Success: Added CSM role to improve retention and expansion metrics
Workforce Planning Updates
▸
Q2 Hiring Plan: 6 additional roles approved (4 Engineering, 1 Sales, 1 CS)
▸
Budget Status: Headcount spend at 94% of Q1 forecast
▸
Location Strategy: 73% US-based, 27% international (Canada, UK, Germany)
▸
Remote Work: 89% fully remote, 11% hybrid (SF office)
Note: All metrics as of March 31, 2026 | Data source: HRIS and ATS systems

## Slide 4
Organization Chart and Headcount
Current Reporting Structure — Total Headcount: 45
CEO (1)
VP Engineering (1)
VP Product (1)
VP Sales (1)
CFO (1)
VP People (1)
Eng. Managers (3)
Senior Eng. (5)
Engineers (6)
DevOps (2)
Product Mgrs (3)
Designers (3)
UX Research (1)
Sales Mgr (1)
Enterprise AE (3)
Mid-Mkt AE (3)
SDRs (3)
Controller (1)
Finance Analyst (1)
HRBP (1)
Recruiting (2)
Headcount Breakdown
Engineering
18
Sales
12
Product & Design
7
Finance
2
People (HR)
3
Executive Team
1
TOTAL
45
Key Notes
• Customer Success (2) reports to VP Sales
• Engineering Managers have 5-6 direct reports each
• Sales Manager oversees 9 AEs + 3 SDRs
• No open VP-level positions
Verification: Engineering (18) + Sales (12) + Product/Design (7) + Finance (2) + People (3) + Executive (1) + CS (2) = 45 Total

## Slide 5
Hiring Progress
Q1 2026 Recruitment Status by Function
Engineering
4/4 Filled
Senior Backend Engineer
Start: Jan 15 | Time-to-fill: 38 days
ML Engineer
Start: Feb 1 | Time-to-fill: 52 days
DevOps Engineer
Start: Feb 20 | Time-to-fill: 41 days
Frontend Engineer
Start: Mar 8 | Time-to-fill: 35 days
Open Roles:
1 (Principal Engineer)
Product
1/1 Filled
Product Manager — Platform
Start: Jan 22 | Time-to-fill: 45 days
Open Roles:
1 (PM — Growth)
Deferred to Q2 pending roadmap
Sales
2/3 Filled
Enterprise AE — East
Start: Jan 8 | Time-to-fill: 29 days
Enterprise AE — West
Start: Feb 15 | Time-to-fill: 44 days
Mid-Market AE
Status: Offer extended, pending acceptance
Open Roles:
0
HR / Recruiting
Talent Partner
Start: Feb 1 | 1/1 filled
Complete
Pipeline Summary
47
Total Applicants
12
In Interview
3
Offers Out
Q1 Target: 11 hires | Achieved: 8 hires (72%) | Carryover to Q2: 3 roles

## Slide 6
Retention and Attrition
Q1 2026 Workforce Stability Analysis
Q1 Departures
Senior Frontend Engineer
Engineering • 2.5 years tenure
Voluntary
Reason: Accepted role at larger tech company
Mid-Market AE
Sales • 1.8 years tenure
Voluntary
Reason: Career change to different industry
Product Designer
Product • 3.2 years tenure
Voluntary
Reason: Relocated to different city
Attrition Metrics
6.7%
Voluntary Attrition
3 of 45 employees
0%
Involuntary Attrition
No terminations
2.4 yr
Avg. Tenure at Exit
Industry avg: 2.1 yr
Retention by Function
Within Benchmark
6.7% below SaaS industry average of 13-18%
Monitoring Required
2 of 3 departures from Engineering
Action Taken
Exit interviews completed; feedback reviewed

## Slide 7
Performance and Talent Review
Q1 Performance Cycle and Talent Quality Assessment
Q1 Performance Review Cycle
Self-Assessment Completion
94%
Manager Review Completion
92%
Calibration Sessions Held
5 of 5
Final Reviews Approved
100%
Average Review Cycle Time
18 days
Performance Distribution
Exceeds Expectations
18%
Meets Expectations
67%
Developing
12%
Needs Improvement
3%
Distribution aligns with target bell curve (15-20% exceeds, 65-70% meets)
High-Potential Talent
8 Employees Identified
Calibration sessions identified top performers ready for accelerated development and expanded scope.
Engineering: 4
Product: 2
Sales: 1
Finance: 1
Individual development plans created for all 8
Succession Planning
3 Critical Roles Identified
VP Engineering, VP Sales, VP Product
Internal Candidates
2 potential successors identified for VP Engineering
Development Actions
Leadership training, cross-functional projects, mentorship
Next Review Cycle: Q3 2026 (mid-year) | Calibration Lead: VP People with functional VPs

## Slide 8
Employee Programs / Organizational Support
Q1 HR Operational Updates and Enablement Initiatives
Onboarding Improvements
Structured 30-60-90 Day Plan
Standardized for all new hires with clear milestones
Buddy Program Launch
8 experienced employees trained as onboarding buddies
Manager Check-in Template
Weekly touchpoints for first 90 days
New Hire Survey
30-day feedback collection (avg score: 4.2/5.0)
Manager Enablement
Manager Training Series
3 sessions completed: Feedback, 1:1s, Goal Setting
Manager Handbook Update
Revised with new processes and templates
People Manager Community
Monthly peer learning sessions (12 managers)
Engagement Initiatives
Quarterly All-Hands
March 15 — 89% attendance, CEO roadmap presentation
Team Offsites
Engineering (Feb), Sales (Mar), Product (planned Q2)
Pulse Survey
Quarterly engagement pulse (response rate: 78%)
Recognition Program
Peer-to-peer recognition platform launched
Policy Refresh
Remote Work Policy
Updated to clarify expectations and equipment
PTO Policy
Simplified accrual and rollover rules
Parental Leave
Under review for Q2 enhancement
Program Owner: VP People | Support: HRBP, Office Manager | Budget Utilization: 87% of Q1 allocated

## Slide 9
Risks and Watch Items
People-Related Risks Requiring Monitoring
1
Hiring Delays
Risk: Three roles from Q1 plan remain unfilled (Principal Engineer, Enterprise AE, CSM). Extended vacancies may impact product roadmap and revenue targets.
Impact: Medium — Engineering capacity constraints, Sales pipeline coverage gaps
Mitigation: Increased sourcing budget, engaged external agency for senior engineering role, accelerated interview process
Medium Priority
Target resolution: Q2
2
Team Bandwidth
Risk: Engineering team operating at high capacity with 1:9 manager-to-IC ratio. Risk of burnout and reduced quality if sustained.
Impact: Medium-High — Delivery delays, attrition risk, technical debt accumulation
Mitigation: Prioritize Engineering Manager hire in Q2, review project scope with Product, implement workload monitoring
High Priority
Escalated to leadership
3
Manager Load
Risk: Senior managers (VP Eng, VP Sales) carrying heavy spans of control. Limited time for strategic work and team development.
Impact: Medium — Reduced strategic focus, slower decision-making, manager fatigue
Mitigation: Evaluate need for Director-level layer, delegate operational tasks, prioritize leadership hires
Medium Priority
Under review
4
Org Structure Pressure
Risk: Rapid growth (8 new hires in Q1) straining existing communication channels and decision-making processes.
Impact: Low-Medium — Information silos, slower cross-functional collaboration
Mitigation: Document decision-making frameworks, enhance All-Hands communication, implement cross-functional project teams
Low Priority
Monitor quarterly
Risk Review Process: Monthly leadership sync | Owner: VP People | Next Review: April 30, 2026

## Slide 10
Next Quarter Priorities
Q2 2026 HR Strategic Focus Areas
1
Complete Q1 Carryover Hiring
Fill 3 remaining Q1 roles plus 6 new Q2 approved positions:
Principal Engineer (priority)
Enterprise AE + CSM
4 Engineering (Q2 plan)
1 Sales + 1 CS (Q2 plan)
Target: 9 hires | Budget: $1.2M
2
Address Bandwidth Risks
Implement immediate actions to reduce team pressure:
Hire Engineering Manager (Q2)
Review project scope with Product
Implement workload tracking
Manager 1:1 focus on burnout
Owner: VP People + VP Eng
3
Launch Development Programs
Activate talent development initiatives:
High-potential development tracks
Technical mentorship program
Leadership training (Level 2)
Career pathway documentation
Owner: HRBP + functional VPs
Additional Q2 Initiatives
▸
Compensation Review: Market analysis for Engineering and Sales
▸
Benefits Enhancement: Parental leave policy update
▸
Engagement Survey: Comprehensive annual survey (April)
▸
HRIS Upgrade: Evaluate new platform capabilities
Success Metrics
▸
Hiring: 9 of 9 roles filled (100%)
▸
Attrition: Maintain < 10%
▸
Engagement: Survey response > 80%
▸
Development: 8 high-potential plans activated
Q2 Planning Timeline
April: Kickoff | May: Mid-quarter review | June: Q2 close + Q3 planning
Next Board Review
Q2 2026
Document Status: Departmental Draft — HR Team | Next Update: April 30, 2026 | For: CFO Review & Board Consolidation